## Deployment Plan
De Anza College Campus Wireless | Notes | Estimated Cost to Fully Deploy | Status
(see attached worksheets for details on # of Access points per room and cost)
Deployment Prioritization Plan : Phase I | Roll renovations together
Infrastructure Equipment required to support further deployment | Must be purchased, installed and configured before large scale deployment can be accomplished. | 232542.5 | Per Quote from Aruba; Includes controller/backend failover capability; Professional services for configuring the Airwave management tool; Initial purchaes of 100 Access Points (AP) To be installed based on College's Prioritized Deployment Plan
Estimated additional wiring and power installations | For those areas not wired for wireless or where additional Access Points are required and for the Large outdoor areas such as parking structures and lots - for the life of the project - 10 to 15 years under Measure C | 100000
Refresh of Wireless equipment as technology changes and needs change at the College |  | 100000
Library (main building) | Unles the Library feels there are areas where more coverage is required. If this is the case it will cost about $1200 per Access point and there may be wiring installation costs. Such as in these specific areas: LC123,LC237 - will require 2 Access points each. There will most likely be power and data cabling installation costs. | 4800 | Complete; SL 100808 however may expand to support more users during renovation
Campus Center (16) | Dining Hall and Fireside | 0 | Complete
| 5 conference room areas | 6000
| **Conference rooms A/B | 4800
| Outdoor Patio/table Area | 3600
| Bottom Floor - DASB/Senate Chambers | 4800
KIRSCH (3) | All Classrooms have wireless. Open hallway gathering areas do not have wireless | 3600 | Alpha needs to convert to "Authentication" deployment
SCS (6) | SCS146,SCS202; Downstairs hallway, Upstairs areas | 7200
Science Complex (25) | SC2106,SC2108,SC2116,SC2118,SC2202,SC2204,SC2208,SC2210,SC3101,SC3103,SC1102; Outdoor classroom | 30000
ADMIN (14) | One deployed in ADMIN 109 Conference room - needs 2 more; ADMIN 106 conference room need 2, ADM 119, ADM 101, 102, 103; Lobby | 16800
Need to be prioritized by the College (currently alphabetical)
Deployment Prioritization Plan : Phase II
A Quad (28) + $5,000 for misc. cabling | A25,A72,A51,A52,A65,A71,A81,A86,A91,A93,A94,A31, A11 | 38600
ATC (36) | AT104,AT101,AT102,AT103,AT107,AT202,AT204, AT205,AT301,AT303,AT305,AT307,AT311,AT312, AT313,AT107,AT120 | 43200 | ESTIMATE; Will be done at the rennovation stage and may change since walls are moving
Baldwin Winery (5) | Conference room, Part Time Faculty Area, Finanical Aid area; Print Shop self service area | 6000 | ESTIMATE; Will be done at rennovation stage
CDC (19) | CD1-11,CD1-12,CD16,CD17,CD2-28, CD21,CD25,CD1-10,CD1-13,CD1-14,CD1-15, CD1-16 | 22800 | Need guidance from College - may only want in classrooms; not where children are located
E Quad (20) | E12,E22,E12A,E12B,E12C,E13A,E21,E23 E25,E34,E36 | 24000 | ESTIMATE; Will be done at rennovation stage
East Cottage (4) | Classroom, small class conf room | 4800 | ESTIMATE; Will be done at rennovation stage
FORUM (14) | FOR1,FOR3,FOR4 | 16800
G Quad (13) | G10,G3,G4,G8,G9,G1 | 15600
L Quad (55) + $5,000 for misc. cabling | L42B,L21,L22,L24,L27 L28,L31,L32,L33.L34,L35L42,L43,L45,L46 L48,L49,L61,L62,L63,L65,L66,L73A,L82,L83,L23 L26, L41 (20) | 71000
LCW (3) | LCW16,LCW26(installed) - roll into Library - one renovation project | 3600
Miediated Learning Center (20) | 10 Classrooms, Café area, outdoor area? | 24000 | ESTIMATE
MCC (7) | MCC-10,MCC-17 | 8400 | This building has a planned floor plan change during renovation. The number of Access Points needs to be reassessed. ESTIMATE
Miscellaneous Meeting Rooms around the Campus (4) | MTGRM1,MTGRM2,MTGRM1 MTGRM2 | 4800
* PE Quad (12) + $5,000 for misc. cabling | DWELL/PE,PE650,PE11U,PE12U,PE13,PE62A, PE673 | 19400 | Need to assess locations of infrastructure installed at time of renovation; may require addtional wiring.
Planetarium (3) | Main Theater and Lobby | 3600
* S Quad (59) + $5,000 for misc. cabling | S84,S11,S15,S17,S41,S42,S48,S49,S51,S52,S54, S71,S72,S73,S74,S82,S83,S55,S56,S16,S44,S32, S34,S35 | 70800 | May require infrastructure wiring.
Seminar (8) | SEM1A,SEM3,SEM5,SEM8 | 9600 | This building has a planned floor plan change during renovation. The number of Access Points needs to be reassessed. ESTIMATE
Visual Performing Arts Center (8) | Classroom, Ehuphrat, 3rd Room, (Theater?) | 9600 | ESTIMATE
**Flint Center |  |  | Needs an assessment
Deployment Prioritization Plan : Phase III
Outdoor areas | Flint Parking, Lot C Parking, Stadium, **Flea Market etc. | 40000 | ESTIMATE; Mesh technology?
TOTAL (DOES NOT INCLUDE TAX AND SHIPPING) |  | 950742.5
THERE MAY BE OTHER CONFERENCE ROOMS NOT ON THIS LIST.
MEASURE "C" ALLOCATION |  | 935794 | Need to subtract Overhead charge to this project - min 5.51% leaves $884,231.75
* = Priority per Jeanine Hawk
** = Commercial Entities Use - need to confer with legal counsel

## 10-20
| Room | Max Capacity | Description | Number of Wireless Access Points | Cost per wireless access point
[5 empty] | 802.11a/b/g (AP70) | 802.11n (AP-125ABG) | Discount
√ | CD1-11 | 12 |  | 1 | 600 | 1200
√ | CD1-12 | 12 |  | 1 | 600 | 1200
√ | KC201 | 15 |  | 1 | 600 | 1200
√ | MTGRM1 | 15 |  | 1 | 600 | 1200
√ | MTGRM2 | 15 |  | 1 | 600 | 1200
√ | S84 | 15 |  | 1 | 600 | 1200
√ | CD1-13 | 16 |  | 1 | 600 | 1200
√ | CD1-14 | 16 |  | 1 | 600 | 1200
√ | AT104 | 18 |  | 1 | 600 | 1200
√ | DWELL/PE | 18 |  | 1 | 600 | 1200
√ | A25 | 20 |  | 1 | 600 | 1200
√ | A72 | 20 |  | 1 | 600 | 1200
√ | CD1-15 | 20 |  | 1 | 600 | 1200
√ | CD1-16 | 20 |  | 1 | 600 | 1200
√ | E12 | 20 |  | 1 | 600 | 1200
√ | E22 | 20 |  | 1 | 600 | 1200
√ | L42B | 20 |  | 1 | 600 | 1200
√ | LCW16 | 20 |  | 1 | 600 | 1200
√ | PE650 | 20 |  | 1 | 600 | 1200
√ | SC Outdoor classroom | 20 |  | 1 | 600 | 1200
|  | TOTAL ROOMS = 19 |  | 20 | 12000 | 24000 | 16800

## 21-40
| Room | Max Capacity | Description | Number of Wireless Access Points | Cost per wireless access point
[5 empty] | 802.11a/b/g | 802.11n | Discount
√ | ADM 103 | 40 |  | 2 | 1200 | 2400
√ | ADM 102 | 40 |  | 2 | 1200 | 2400
√ | ADM 101 | 30 |  | 2 | 1200 | 2400
√ | A51 | 30 |  | 2 | 1200 | 2400
√ | A52 | 25 |  | 2 | 1200 | 2400
√ | A65 | 25 |  | 2 | 1200 | 2400
√ | A71 | 30 |  | 2 | 1200 | 2400
√ | A81 | 24 |  | 2 | 1200 | 2400
√ | A86 | 24 |  | 2 | 1200 | 2400
√ | A91 | 30 |  | 2 | 1200 | 2400
√ | A93 | 30 |  | 2 | 1200 | 2400
√ | A94 | 30 |  | 2 | 1200 | 2400
√ | AT101 | 26 |  | 2 | 1200 | 2400
√ | AT102 | 30 |  | 2 | 1200 | 2400
√ | AT103 | 30 |  | 2 | 1200 | 2400
√ | AT107 | 24 |  | 2 | 1200 | 2400
√ | AT202 | 40 |  | 2 | 1200 | 2400
√ | AT204 | 40 |  | 2 | 1200 | 2400
√ | AT205 | 40 |  | 2 | 1200 | 2400
√ | AT301 | 30 |  | 2 | 1200 | 2400
√ | AT303 | 30 |  | 2 | 1200 | 2400
√ | AT305 | 30 | General Lecture | 2 | 1200 | 2400
√ | AT307 | 35 |  | 2 | 1200 | 2400
√ | AT311 | 30 |  | 2 | 1200 | 2400
√ | AT312 | 32 |  | 2 | 1200 | 2400
√ | AT313 | 30 |  | 2 | 1200 | 2400
√ | CD16 | 40 |  | 2 | 1200 | 2400
√ | CD17 | 30 |  | 2 | 1200 | 2400
√ | CD2-28 | 25 |  | 2 | 1200 | 2400
√ | CD21 | 40 |  | 2 | 1200 | 2400
√ | CD25 | 40 |  | 2 | 1200 | 2400
√ | E12A | 24 | General Classroom | 2 | 1200 | 2400
√ | E12B | 24 | General Classroom | 2 | 1200 | 2400
√ | E12C | 24 | General Classroom | 2 | 1200 | 2400
√ | E13A | 24 | General Classroom | 2 | 1200 | 2400
√ | E21 | 24 |  | 2 | 1200 | 2400
√ | E23 | 24 |  | 2 | 1200 | 2400
√ | E25 | 35 | General Classroom | 2 | 1200 | 2400
√ | E34 | 40 | General Classroom | 2 | 1200 | 2400
√ | E36 | 40 | General Lecture | 2 | 1200 | 2400
√ | G10 | 40 | General Classroom | 2 | 1200 | 2400
√ | G3 | 40 | General Classroom | 2 | 1200 | 2400
√ | G4 | 40 | General Classroom | 2 | 1200 | 2400
√ | G8 | 24 |  | 2 | 1200 | 2400
√ | G9 | 24 | General Classroom | 2 | 1200 | 2400
√ | KC120 | 32 |  | 2 | 1200 | 2400
√ | KC239 | 32 |  | 2 | 1200 | 2400
√ | L21 | 40 | General Classroom | 2 | 1200 | 2400
√ | L22 | 40 | General Classroom | 2 | 1200 | 2400
√ | L24 | 40 | General Classroom | 2 | 1200 | 2400
√ | L27 | 40 | General Classroom | 2 | 1200 | 2400
√ | L28 | 40 | General Classroom | 2 | 1200 | 2400
√ | L31 | 40 | General Classroom | 2 | 1200 | 2400
√ | L32 | 40 | General Classroom | 2 | 1200 | 2400
√ | L33 | 40 | General Classroom | 2 | 1200 | 2400
√ | L34 | 40 | General Classroom | 2 | 1200 | 2400
√ | L35 | 35 | General Classroom | 2 | 1200 | 2400
√ | L42 | 40 | General Classroom | 2 | 1200 | 2400
√ | L43 | 35 | General Classroom | 2 | 1200 | 2400
√ | L45 | 30 | General Classroom | 2 | 1200 | 2400
√ | L46 | 30 | General Classroom | 2 | 1200 | 2400
√ | L48 | 35 | General Classroom | 2 | 1200 | 2400
√ | L49 | 35 | General Classroom | 2 | 1200 | 2400
√ | L61 | 40 | General Classroom | 2 | 1200 | 2400
√ | L62 | 40 | General Classroom | 2 | 1200 | 2400
√ | L63 | 40 | General Classroom | 2 | 1200 | 2400
√ | L65 | 40 | General Classroom | 2 | 1200 | 2400
√ | L66 | 40 | General Classroom | 2 | 1200 | 2400
√ | L73A | 35 | General Classroom | 2 | 1200 | 2400
√ | L82 | 35 | General Classroom | 2 | 1200 | 2400
√ | L83 | 40 | General Classroom | 2 | 1200 | 2400
√ | LC123 | 30 |  | 2 | 1200 | 2400
√ | LC237 | 25 |  | 2 | 1200 | 2400
√ | LCW26 | 32 |  | 2 | 1200 | 2400
√ | PE11U | 30 |  | 2 | 1200 | 2400
√ | PE12U | 35 | General Classroom | 2 | 1200 | 2400
√ | PE13 | 22 |  | 2 | 1200 | 2400
√ | PE62A | 40 |  | 2 | 1200 | 2400
√ | PE673 | 40 |  | 2 | 1200 | 2400
√ | S11 | 35 |  | 2 | 1200 | 2400
√ | S15 | 35 |  | 2 | 1200 | 2400
√ | S17 | 35 |  | 2 | 1200 | 2400
√ | S41 | 36 | General Classroom | 2 | 1200 | 2400
√ | S42 | 30 |  | 2 | 1200 | 2400
√ | S48 | 30 |  | 2 | 1200 | 2400
√ | S49 | 36 | General Classroom | 2 | 1200 | 2400
√ | S51 | 30 |  | 2 | 1200 | 2400
√ | S52 | 30 |  | 2 | 1200 | 2400
v | S54 | 40 | General Lecture | 2 | 1200 | 2400
√ | S71 | 30 | General Classroom | 2 | 1200 | 2400
v | S72 | 35 | General Classroom | 2 | 1200 | 2400
√ | S73 | 30 |  | 2 | 1200 | 2400
√ | S74 | 30 |  | 2 | 1200 | 2400
√ | S82 | 40 |  | 2 | 1200 | 2400
√ | S83 | 40 |  | 2 | 1200 | 2400
√ | SC2106 | 32 |  | 2 | 1200 | 2400
√ | SC2108 | 28 |  | 2 | 1200 | 2400
√ | SC2116 | 26 |  | 2 | 1200 | 2400
√ | SC2118 | 26 |  | 2 | 1200 | 2400
√ | SC2202 | 28 |  | 2 | 1200 | 2400
√ | SC2204 | 28 |  | 2 | 1200 | 2400
√ | SC2208 | 28 |  | 2 | 1200 | 2400
√ | SC2210 | 28 |  | 2 | 1200 | 2400
√ | SC3101 | 32 |  | 2 | 1200 | 2400
√ | SC3103 | 32 |  | 2 | 1200 | 2400
√ | SEM1A | 40 | General Classroom | 2 | 1200 | 2400
√ | SEM3 | 30 | General Classroom | 2 | 1200 | 2400
√ | SEM5 | 30 | General Classroom | 2 | 1200 | 2400
√ | SEM8 | 30 | General Classroom | 2 | 1200 | 2400
|  | TOTAL ROOMS = 107 |  | 218 | 130800 | 261600 | 183120

## 70-80
| Room | Max Capacity | Description | Number of Wireless Access Points | Cost per wireless access point
[5 empty] | 802.11a/b/g | 802.11n | Discount
√ | S55 | 75 | General Lecture | 4 | 2400 | 4800
√ | S56 | 75 | General Lecture | 4 | 2400 | 4800
√ | CD1-10 | 80 | Lecture Classroom | 3 | 1800 | 3600
√ | G1 | 80 | Lecture Classroom | 3 | 1800 | 3600
√ | MCC-17 | 80 | Lecture Classroom | 3 | 1800 | 3600
√ | S16 | 80 | Lecture Classroom | 3 | 1800 | 3600
√ | S44 | 80 | Lecture Classroom | 3 | 1800 | 3600
√ | ADM 119 | 80 | lecture Classroom | 3 | 1800 | 3600
|  | TOTAL ROOMS = 8 |  | 26 | 15600 | 31200 | 21840

## Lecture Hallsconf rm
| Room | Max Capacity | Description | Number of Wireless Access Points | Cost per wireless access point
[5 empty] | 802.11a/b/g | 802.11n | Discount
√ | A31 | 60 | Classroom (Row - Tiered Seating/ Theater) | 4 | 2400 | 4800
√ | AT107 | 24 | Classroom (Row - Tiered Seating/ Theater) | 2 | 1200 | 2400
√ | AT120 | 125 | Classroom (Row - Tiered Seating/ Theater) | 5 | 3000 | 6000
√ | FOR1 | 324 | Classroom (Row - Tiered Seating/ Theater) | 6 | 3600 | 7200
√ | FOR3 | 106 | Classroom (Row - Tiered Seating/ Theater) | 4 | 2400 | 4800
√ | FOR4 | 106 | Classroom (Row - Tiered Seating/ Theater) | 4 | 2400 | 4800
√ | L23 | 57 | Classroom (Row - Tiered Seating/ Theater) | 3 | 1800 | 3600
√ | L26 | 69 | Classroom (Row - Tiered Seating/ Theater) | 3 | 1800 | 3600
√ | MCC-10 | 68 | Classroom (Row - Tiered Seating/ Theater) | 3 | 1800 | 3600
√ | MCC-17 | 80 | Classroom (Row - Tiered Seating/ Theater) | 4 | 2400 | 4800
√ | S32 | 123 | Classroom (Row - Tiered Seating/ Theater) | 5 | 3000 | 6000
√ | S34 | 93 | Classroom (Row - Tiered Seating/ Theater) | 4 | 2400 | 4800
√ | S35 | 60 | Classroom (Row - Tiered Seating/ Theater) | 3 | 1800 | 3600
√ | SC1102 | 100 | Classroom (Row - Tiered Seating/ Theater) | 4 | 2400 | 4800
√ | KC112 | 50 | Classroom (Reception Style - Tables & Chairs) | 2 | 1200 | 2400
√ | KC113 | 50 | Classroom (Reception Style - Tables & Chairs) | 2 | 1200 | 2400
√ | KC115 | 100 | Classroom (Reception Style - Tables & Chairs) | 4 | 2400 | 4800
√ | FIRESD | 120 | Conference Room (Rounds of 10) | 4 | 2400 | 4800
√ | CONFA | 0 | Conference Room | 2 | 1200 | 2400
√ | CONFB | 0 | Conference Room | 2 | 1200 | 2400
√ | DONBAU | 0 | Conference Room | 1 | 600 | 1200
√ | LAMARGTA | 0 | Conference Room | 1 | 600 | 1200
√ | MAINRM | 0 | Conference Room | 1 | 600 | 1200
√ | MTGRM1 | 0 | Conference Room | 1 | 600 | 1200
√ | MTGRM2 | 0 | Conference Room | 1 | 600 | 1200
√ | SANTACZ | 0 | Conference Room | 1 | 600 | 1200
√ | STAFFLNGE | 0 | Conference Room | 1 | 600 | 1200
√ | ADM106 | 45 | Conference Room - Table w/chairs | 2 | 1200 | 2400
√ | ADM109 | 67 | Conference Room - Table w/chairs | 3 | 1800 | 3600
√ | ELCLEM | 0 | Conference Room - Table w/chairs | 1 | 600 | 1200
√ | SCS146 | 1 | Conference Room - Table w/chairs | 1 | 600 | 1200
√ | SCS202 | 1 | Conference Room - Table w/chairs | 1 | 600 | 1200
√ | CC |  | Bottom Floor - DASB/Senate Chambers | 4 | 2400 | 4800
√ | CC |  | Outdoor Patio area | 3 | 1800 | 3600
√ | ADM Lobby |  | Lobby area | 1 | 600 | 1200
√ | Baldwin Winery |  | Print shop | 1 | 600 | 1200
√ | Planetarium |  | Theater and Lobby | 3 | 1800 | 3600
| A11 | 150 |  | 4 | 2400 | 4800
|  | TOTAL ROOMS = 37 |  | 101 | 60600 | 121200 | 84840
A11